## Project schedule
| Group B Team 4: Project Planner for Prototyping and Systems Engineering. Focus: Autonomous Vehicle Design and Testing | [6 empty] | Project start: | [7 empty] | 2025-04-07 | [12 empty] | Project report submission timeline: Tue,07.08.2025 [MM/DD/YYYY]
| Project Contributors: Chimezie, Daniel Chidi (Mat. Nr. 1230515) - Member / Coordinator Cho, Bertrand Mungu ( Mat. Nr. 2220052) - Member Ghimire,Riwaj ( Mat. Nr. 1232171) - Member | [6 empty] | Display week: | [7 empty] | 1
| Project supervision and directions: Professor Stefan Henkler / Gido Wahrmann / Faezeh Pasandideh | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26
| TASK | ASSIGNED TO | SUPPORTED BY | PROGRESS | START | END | time axis 2025-04-07 to 2025-06-01
[8 empty] | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Project Initialization and Planning
| Project goals and scope definition | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-07 | 2025-04-08 | 2
| Research similar systems | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-08 | 2025-04-10 | 3
| Define system requirements (hardware/software) | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-10 | 2025-04-12 | 3
| Budget and resource planning | Cho, Bertrand M. | Ghimire Riwaj / Chimezie Daniel C. | 100% | 2025-04-12 | 2025-04-13 | 2
| Risk assessment | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-13 | 2025-04-14 | 2
System Design
| Block diagram/system architecture | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-14 | 2025-04-19 | 6
| Sensor and actuator selection | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-14 | 2025-04-15 | 2
| Circuit schematic design | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-14 | 2025-04-16 | 3
| Mechanical chassis design | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-14 | 2025-04-19 | 6
| Power supply holder design | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-14 | 2025-04-16
| Pin mapping for Arduino Uno R4 | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-14 | 2025-04-16 | 3
Hardware Procurement and Assembly
| Order and replacement for components (Arduino Uno R4, sensors, motors ) | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-21 | 2025-04-21 | 1
| Assemble the chassis | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-21 | 2025-04-21 | 1
| Mount motors and wheels | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-21 | 2025-04-21 | 1
| Connect sensors (IR, Ultrasonic, Colour.) | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-21 | 2025-04-21 | 1
| Connect motor drivers and power modules | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-21 | 2025-04-21 | 1
| Wiring and cable management | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-21 | 2025-04-27 | 7
Software Development
| Arduino IDE setup | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-28 | 2025-04-28 | 1
| Write/test modules: | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-28 | 2025-05-03 | 6
| >> Line-following using IR sensors | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-28 | 2025-05-01 | 4
| >> Obstacle avoidance using ultrasonic sensor | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-28 | 2025-05-01 | 4
| >> Motor control (PWM, direction) | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-28 | 2025-05-01 | 4
| >> Colour detection | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-28 | 2025-05-03
| Integrate modules into main control loop | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-04-28 | 2025-05-03
| PID and Logic tuning for line-following | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-04-28 | 2025-05-03
| Fail-safe and debugging (routine process) | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-04-28 | 2025-06-23
Integration and Testing
| Combine hardware and software | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-05-05 | 2025-05-05 | 1
| Functional testing of all subsystems | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-05-05 | 2025-05-05 | 1
| Field tests: | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-05-05 | 2025-05-05 | 1
| >> Line-following accuracy | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-05-05 | 2025-05-28 | 24
| >>Obstacle detection responsiveness | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-05-05 | 2025-05-25 | 21
| >>Route completion success rate | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-05-05 | 2025-06-14
| Debugging and iteration (routine process) | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-05-05 | 2025-06-22
| Power efficiency testing | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-05-05 | 2025-05-10
Documentation
| Wiring diagrams and circuit explanations | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-05-12 | 2025-05-12 | 1
| Code documentation (comments, flowcharts) | Ghimire Riwaj | Cho, Bertrand M. / Chimezie Daniel C. | 100% | 2025-05-12 | 2025-05-15 | 4
| Test results and data logs | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-05-05 | 2025-06-23 | 50
| User manual or usage instructions | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-05-05 | 2025-06-04 | 31
| Final report | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-05-12 | 2025-07-06 | 56
Presentation and Delivery
| Prepare demo video or live demo (Competition Day) * 1st position for Group A and B Contest.*** | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-06-23 | 2025-06-23 | 1
| Slides and presentation materials | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-06-23 | 2025-06-23 | 1
| Q&A preparation for inputs and future advances | Cho, Bertrand M. | Chimezie, Daniel C./Ghimire Riwaj | 100% | 2025-06-23 | 2025-06-23 | 1
| Final handover of project | Chimezie, Daniel C. | Cho, Bertrand M. / Ghimire Riwaj | 100% | 2025-07-06 | 2025-07-08 | 2
Insert new rows ABOVE this one